## Sheet1
Robotex Activity Chart
Task |  | Deliverable/Milestone |  | Duration (Days) | Dependency | Status | Staff
|  | Semi | Final |  |  |  | SE Project Manager | Programmer | DB Specialist | Customer Specialist
T1 | Preliminary Requirement analysis |  |  | 7d |  |  | √ | √ | √ | √
T2 | First draft system specification | D1. Report |  | 3d |  |  | √ | √ | √
T3 | Meeting with client | ◄ |  | 1d |  |  | √ | √ | √ | √
T4 | Use case diagram |  |  | 3d | T1,T3 |  | √
T5 | ER diagram |  |  | 7d | T4 |  |  |  | √
T6 | Sequence diagram |  |  | 5d | T4 |  |  | √
T7 | Class diagram |  |  | 7d | T5,T6 |  | √
T8 | Meeting with client | ♦ |  | 1d | T7 |  | √ | √ | √ | √
T9 | Accommodate Client comments to UML diagrams |  |  | 2d |  |  | √ | √
T10 | Transform ERD to DB Schema |  |  | 5d |  |  |  |  | √
T11 | Database Creation from DB Schema |  |  | 7d | T5 |  |  |  | √
T12 | Load example data to DB |  |  | 1d | T11 |  |  |  | √
T13 | Check DB validity |  |  | 3d | T12 |  |  | √
T14 | Front end design |  |  | 7d |  |  |  | √
T15 | Front end implementation |  |  | 10d | T14 |  |  | √
T16 | DB connection |  |  | 5d | T13,T15 |  |  |  | √
T17 | Combine all implementations |  | ♦ | 1d |  |  | √ | √ | √ | √
T19 | Testing |  |  |  | T17 |  |  |  | √
T20
T21
T22
T23
T24